## Executive_KPI
KPI | Value
Planned Progress | 83
Actual Progress | 30
Design Progress | 98
Procurement Progress | 99
Execution Progress | 65
T&C Progress | 24
Open Risks | 6

## Design_Tracker
Description | Total Nos | Submitted for Approval | CODE F | CODE A | CODE B | CODE C | Balance for submission | Remarks
PHASE 1 & 2
Electrical | 113 | 2 | 97 | 8 | 5 |  | 1
HVAC | 74 | 7 | 59 | 3 | 2 |  | 3
HAC | 4 |  |  | 1 |  |  | 3
UTILITY | 6 |  | 5 |  | 1
FPS | 21 | 2 | 15 | 4
BIM (LOD 400) | 5 | 4 |  |  |  |  | 1
Common | 1 |  |  |  | 1
| 224 | 15 | 176 | 16 | 9 |  | 8

## TDS_Tracker
Description | Total Nos | Under Jacobs' review | CODE F | CODE A | CODE B | CODE C | Balance for submission
HVAC | 59 | 0 | 54 | 4 | 1 | 0 | 0
Electrical | 33 | 2 | 30 | 0 | 1 | 0 | 0
FPS | 33 | 0 | 24 | 8 | 1 | 0 | 0
FAS | 8 | 0 | 8 | 0 | 0 | 0 | 0
PHE | 2 | 0 | 1 | 1 | 0 | 0 | 0
NMDC-02 TDS | 135 | 2 | 117 | 13 | 3 | 0 | 0

## Procurement
Package | Status | Completion %
PDU | Delayed | 70
UPS | Delivered | 100
Battery | Delivered | 100
Chiller | Delivered | 100
Busduct | Delivered | 100
DG | Delivered | 100
Transformer | Delivered | 100
Panels | Delivered | 100
Fire Alarm | Delivered | 95

## Construction
Floor | Progress
Ground Floor | 85
First Floor | 78
Second Floor | 70
Third Floor | 62
Fourth Floor | 55

## Testing_Commissioning
System | Completion %
UPS | 35
PDU | 20
Chiller | 28
Fire Alarm | 15
BMS | 22
DG | 40
Transformer | 50

## Milestones
Milestone | Baseline Date | Forecast Date | Status
Floor Readiness | 2026-07-01 | 2026-07-10 | Delayed
DG Installation | 2026-07-10 | 2026-07-25 | Delayed
PDU Installation | 2026-07-15 | 2026-07-30 | Delayed
IST Phase-1 | 2026-08-01 | 2026-08-20 | Pending
IST Phase-2 | 2026-08-15 | 2026-09-05 | Pending

## Manpower
Date | Mechanical | Electrical | Housekeeping | Common | Subcontractors | Yard Activities | Total
2026-05-26 | 78 | 336 | 17 | 11 | 50 | 81 | 573
2026-05-27 | 78 | 344 | 17 | 13 | 50 | 108 | 610
2026-05-28 | 58 | 226 | 17 | 12 | 50 | 90 | 453
2026-05-29 | 59 | 286 | 17 | 12 | 50 | 96 | 520
2026-05-30 | 61 | 340 | 17 | 11 | 50 | 104 | 583
2026-05-31 | 28 | 336 | 17 | 10 | 50 | 72 | 513
2026-06-01 | 61 | 326 | 17 | 12 | 50 | 91 | 557
2026-06-02 | 61 | 336 | 17 | 13 | 50 | 100 | 577

## Impact_Register
Activity | Owner | Impact Days | Status | Impact Category | Mitigation Action
PDU Delivery Delay | Vendor | 20 | Open | Procurement | Expedite vendor delivery
Fire Rated Door Installation | C&I | 15 | Open | Construction | Increase installation crew
Rolling Shutter Installation | C&I | 10 | Open | Construction | Prioritize critical areas
DG Building Clearance | Civil | 18 | Open | Civil | Accelerate authority approvals
Fuel Piping Completion | Mechanical | 12 | Open | Mechanical | Deploy additional manpower
GIS Shutdown Rescheduling | Client | 25 | Open | External Dependency | Coordinate with client
HSD Yard Readiness | Civil | 15 | Open | Civil | Expedite yard completion
Electrical Room Access | Civil | 8 | Closed | Construction | Completed
Network Cable Tray Approval | Engineering | 6 | Closed | Design | Approval received
L2 Floor Readiness | Civil | 10 | Open | Construction | Accelerate finishing works
AC/LC Flushing Readiness | Mechanical | 8 | Open | Mechanical | Increase resources
Battery Room Readiness | Civil | 10 | Open | Construction | Fast-track room handover

## Risk_Register
Risk | Probability | Impact
PDU Delivery Delay | 5 | 5
DG Building Clearance | 4 | 5
Fire Rated Door Delay | 4 | 4
HSD Yard Delay | 4 | 4
Fuel Piping Delay | 3 | 3
GIS Shutdown Delay | 5 | 5

## SCurve
Week | Baseline | Revised | Actual
Oct | 1 | 1 | 1
Nov | 5 | 4 | 3
Dec | 12 | 10 | 7
Jan | 22 | 18 | 12
Feb | 35 | 28 | 18
Mar | 50 | 40 | 22
Apr | 65 | 52 | 25
May | 78 | 65 | 27
Jun | 88 | 75 | 28
Jul | 94 | 85 | 29
Aug | 98 | 92 | 30
Sep | 100 | 100 | 30